## Project schedule
| Online Book Store | [5 empty] | Project start: | [7 empty] | 2024-05-24
| ITWorks | Project lead |  |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-05-20 to 2024-07-14
 | time axis 2024-05-20 to 2024-07-14
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Evaluate
| Deliverables | Development Leader | 80% | 2024-05-24 | 2024-05-25 | 2
| Determine Milestones |  | 50% | 2024-05-25 | 2024-05-26 | 2
| Work Breakdown |  | 0% | 2024-05-26 | 2024-05-29 | 4
| Risk Analysis |  | 100% | 2024-05-26 | 2024-05-31 | 6
| Personnel Selection and Evaluation |  | 0% | 2024-05-26 | 2024-05-28 | 3
Initial Coding
| Recreate Database | Team Developer | 0% | 2024-06-02 | 2024-06-03 | 2
| Debug and fix initial code |  | 0% | 2024-06-04 | 2024-06-09 | 6
|  |  | 0% | 2024-06-09 | 2024-06-09 | 1
| Code Documentation |  | 0% | 2024-06-09 | 2024-06-09 | 1
|  |  | 0% | 2024-06-09 | 2024-06-09 | 1
Re-engineering
|  |  | 0% | 2024-06-08 | 2024-06-08 | 1
|  |  | 0% | 2024-06-08 | 2024-06-08 | 1
|  |  | 0% | 2024-06-08 | 2024-06-08 | 1
|  |  | 0% | 2024-06-08 | 2024-06-08 | 1
| UML Documentation |  | 0% | 2024-06-08 | 2024-06-08
Testing
|  |  | 0% | 2024-06-10 | 2024-06-13 | 4
|  |  | 0% | 2024-06-13 | 2024-06-17 | 5
|  |  | 0% | 2024-06-18 | 2024-06-21 | 4
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]